## Sheet1
Date | Time | Comment | Member
2014-02-03 | 15:24 | Revieved specifications from Prof. Gruner | Group
2014-02-03 |  | Created github repo | Mathys
2014-02-04
2014-02-05
2014-02-06
2014-02-07
2014-02-08
2014-02-09
2014-02-10
2014-02-11
2014-02-12 | 9:30 | Meeting with client to introduce new team member and discuss project | Group
2014-02-12 | 10:04 | Received email with templates | Group
2014-02-13
2014-02-14 | 9:09 | Sent technical questions to client | Alfred
2014-02-14 | 10:29 | Client sent technical questions to UP IT department
2014-02-15
2014-02-16 |  | Added Alfred and Carlo to github repo | Mathys
2014-02-17
2014-02-18 | 8:43 | Contacted Dr. Fritz Solms with regards to project templates
2014-02-19 | 13:40 PM | Google calander created | Mathys
2014-02-20
2014-02-21
2014-02-22
2014-02-23
2014-02-24 |  | Decied on work divisions for SRS document | Group
2014-02-24 |  | Started team porfolio on repo. | Mathys
2014-02-25 | 13:15 PM | Enquired client about IT department feed back not received | Mathys
2014-02-25 | 13:33 PM | Client informs group that process flow and information description is required | Group
2014-02-26
2014-02-27
2014-02-28 | 10:13 | Sent more IT technical specs for system | Mathys
2014-03-01
2014-03-02
2014-03-03 | 13:01 | Client sent more information to UP IT department
2014-03-04
2014-03-05
2014-03-06
2014-03-07 |  | Group got access to SSFM lab from Prof. Gruner | Group
2014-03-08
2014-03-09
2014-03-10
2014-03-11
2014-03-12
2014-03-13 | 7:47 | Enquired client about IT department feed back not received
2014-03-14 | 9:39 | Client still waiting for response from IT department
2014-03-15
2014-03-16
2014-03-17 | 8:08 | Francois DeJager respondes to client asking for more time
2014-03-18
2014-03-19
2014-03-20
2014-03-21
2014-03-22 | 13:46 | Sent first draft of SRS document for client review | Mathys
2014-03-23
2014-03-24
2014-03-25
2014-03-26
2014-03-27
2014-03-28
2014-03-29
2014-03-30
2014-03-31
2014-04-01
2014-04-02
2014-04-03
2014-04-04
2014-04-05 | 15:17 PM | Request for group meeting at SSFM lab on 7-April | Mathys
2014-04-06 |  | Request to change time or date of meeting. Meeting time changed 11:50 | Alfred
2014-04-07 |  | Group meeting. | Group
2014-04-07 |  | Meeting arrangement made to meet every Monday and Friday to discuss project | Group
2014-04-08
2014-04-09
2014-04-10
2014-04-11 | 8:30 | Group meeting | Group
2014-04-12
2014-04-13
2014-04-14 | 11:30 | Group meeting | Group
2014-04-15
2014-04-16
2014-04-17
2014-04-18 | 8:30 | Group meeting | Group
2014-04-19
2014-04-20
2014-04-21 | 11:30 | Group meeting | Group
2014-04-22
2014-04-23
2014-04-24
2014-04-25 | 8:30 | Group meeting. Carlo cannot make it due to family emergency | Group
2014-04-26
2014-04-27
2014-04-28 | 11:30 | Group meeting | Group
2014-04-29
2014-04-30
2014-05-01
2014-05-02 | 8:30 | Group meeting | Group
2014-05-03
2014-05-04
2014-05-05 | 11:30 | Group meeting | Group
2014-05-06
2014-05-07
2014-05-08
2014-05-09 | 8:30 | Group meeting | Group
2014-05-10
2014-05-11
2014-05-12 | 11:30 | Group meeting | Group
2014-05-12 |  | Added iteration 1 documents and started resturcing of project documentation on repo | Mathys
2014-05-13
2014-05-14 | 12:24 | Lab access permission sent to Prof. Gruner for Miss Stacy | Mathys
2014-05-15
2014-05-16 | 8:30 | Group meeting. Miss Stacy attends. | Group
2014-05-16 | 8:30 | Explains her role in the COS 301 projects. Presented project to her.
2014-05-16 | 10:37 | Inform client of progress. Requested meeting next week monday | Mathys
2014-05-17
2014-05-18
2014-05-19 | 11:30 | Group meeting | Group
2014-05-19 | 14:30 PM | Meeting with client about changes to documents and project structure | Group
2014-05-20
2014-05-21
2014-05-22
2014-05-23 | 8:30 | Group meeting. Discussed project presentation | Group
2014-05-23 |  | Completed and demoed first iteration of the project | Group
2014-05-24 | 3:01 PM | Geust lab access request sent to prof. Gruner for Miss Stacy | Mathys
2014-05-24 | 10:29 | Sent first iteration documents for client review | Mathys
2014-05-25
2014-05-26 | 11:30 | Group meeting. Miss Stacy attends. She requires a full timeline and work plan from us | Group
2014-05-27
2014-05-28
2014-05-29 |  | Last day of lectures
2014-05-30 | 12:29 | Sent new project work plan and timeline to Miss Stacy | Mathys
2014-05-31
2014-06-01
2014-06-02
2014-06-03
2014-06-04
2014-06-05
2014-06-06
2014-06-07
2014-06-08
2014-06-09
2014-06-10
2014-06-11 | 11:30 | Request client for meeting on 20 june at 11:15. Client confirmed | Mathys
2014-06-12
2014-06-13
2014-06-14
2014-06-15
2014-06-16 |  | Create Java EE project file structure and SQL script
2014-06-17 |  | Discovered some inconsitanties and lacking of objects in domain objects | Mathys
2014-06-17 |  | Worked on SQL script for database creation | Mathys
2014-06-17 |  | Decided on using XML as content structure in certain databse fields | Group
2014-06-18
2014-06-19
2014-06-20
2014-06-21 |  | End of june exams
2014-06-22 |  | Updated domain objects, refine SQL, converted log to CSV, Created entities | Mathys
2014-06-23 |  | Updated model, SQL, XML Entities, DB Entities, POM.xml | Mathys
2014-06-24
2014-06-25 |  | Added AuditTrail, Notiification, Meeting Management | Alfred
2014-06-26 |  | Added to User Account Management, Added DAOs, and Constants | Mathys
2014-06-27
2014-06-28 |  | Created Integration Tests, in aid of development | Mathys
2014-06-29 |  | Working on User Gateway | Carlo
2014-06-30 |  | Updated template and User Account Management | Mathys
2014-07-01 |  | Completed Grant Holder, Session, updated SQL | Mathys
2014-07-02 |  | Completed initial Dean's Endorsement, did Refractioring to packages | Mathys
2014-07-03 |  | Started Report Services, added to Meeting Management | Alfred
2014-07-03 |  | Added Entities Unit Tests | Mathys
2014-07-04 |  | Added Dependencies, Updated meeting and Report Services | Alfred
2014-07-05 |  | Completed Scrum Reports | Group
2014-07-05 |  | Completed CV, Endorsement, Funding Report Tests | Mathys
2014-07-06 |  | Added DBEntities Factory, Added Builder Factory, Integration of Notification. Refractored Code | Mathys
2014-07-07 |  | Worked on Export, Report Services | Alfred
2014-07-07 |  | User Gateway | Carlo
2014-07-07 |  | Created Unit Tests, Mock Classes | Mathys
2014-07-08 |  | Updated User Gateway, added Login Page | Mathys
2014-07-08 |  | Working on Archival Services | Alfred
2014-07-09 |  | Code refractoring, completed referee service | Mathys
2014-07-10
2014-07-11
2014-07-12
2014-07-13 |  | Added scheduling to archival services | Alfred
2014-07-14 |  | Added primefaces, fixed user gateway, changed session beans | Mathys
2014-07-15 |  | Updated XML schemas | Mathys
2014-07-16 |  | More functionality to Session Class, finished user accounts, login, and backing beans | Mathys
2014-07-17 |  | Added Scrum Reports | Group
2014-07-17 |  | Refactored Management beans and fixed bread crumbs | Mathys
2014-07-18 |  | Notification, Audit Tests | Alfred
2014-07-18 |  | Fixed navigation issues | Mathys
2014-07-19 |  | Meeting management tests, | Alfred
2014-07-20 |  | Added html pages | Carlo
2014-07-20 |  | Made tests passable | Mathys
2014-07-21 |  | Worked on user account management | Mathys
2014-07-22 |  | Navigation update, refactored EJBs, themed bread crumbs | Mathys
2014-07-23 |  | Refactored SQL scripts, application renewal | Mathys
2014-07-24 |  | Added Renewable EJB | Carlo
2014-07-25 |  | Added Activity Diagrams | Carlo
2014-07-25 |  | Grant Holder, CV Management, DRIS Approval tests | Alfred
2014-07-25 |  | Completed Application viewer, HOD pages, Dean's Endorsement pages | Mathys
2014-07-26 |  | Updated new application wizard | Mathys
2014-07-27 |  | Added Diagrams, adjusted DRIS Approval Service | Alfred
2014-07-28 |  | On demand user creation, progress viewer | Mathys
2014-07-29 |  | Did Activity diagrams for Application Progress Viewer | Alfred
2014-07-30 |  | Fixed bugs in application status, refactored database | Mathys
2014-07-31 |  | Added Model Files, Activity diagrams, unit tests | Carlo
2014-07-31 |  | Reconfigured tests | Alfred
2014-07-31 |  | Completed report services, on demand activation pages | Mathys
2014-08-01 |  | Added Domain objects, diagrams | Alfred
2014-08-01 |  | Added diagrams | Carlo
2014-08-01 |  | Demo 2, and documents uploaded | Group
2014-08-02
2014-08-03 |  | Updated security cookies, refactored code, front end templates | Mathys
2014-08-04 |  | Report functionality, jasper dependency | Alfred
2014-08-05 |  | Meeting front end, AppsVSMUS work | Alfred
2014-08-06 |  | Added to meeting management, still buggy | Mathys
2014-08-07 |  | Report front end | Alfred
2014-08-08 |  | Meeting management bugs fixed | Mathys
2014-08-09 |  | Added progress viewer | Mathys
2014-08-10 |  | Report front end | Alfred
2014-08-11 |  | Bugs with reports back end | Alfred
2014-08-12 |  | Updated use case diagrams, domain objects | Mathys
2014-08-13 |  | Unit Tests | Carlo
2014-08-13 |  | More Unit tests | Alfred
2014-08-14 |  | Completed griding for diagrams | Alfred
2014-08-15
2014-08-16 |  | Edited documentation, diagrams | Carlo
2014-08-17 |  | Updated Interface Diagrams, updated report services | Alfred
2014-08-18 |  | Added architectural specs and technologies | Mathys
2014-08-18 |  | Updated tests, completed quality requirements | Alfred
2014-08-19 |  | Added to tactics | Carlo
2014-08-19 |  | Prep work on Import and Export services | Mathys
2014-08-20 |  | Fixed SQL bugs, updated data flow | Mathys
2014-08-20 |  | Updated Report UI | Alfred
2014-08-21 |  | Updated Models | Carlo
2014-08-21 |  | Implemented Report templates | Alfred
2014-08-22 |  | Updated functional documentation, fixed compiler bugs and persistences units | Mathys
2014-08-22 |  | Added diagrams, and updated testing document | Carlo
2014-08-22 |  | Unit test documentation | Alfred
2014-08-22 |  | Demo 3 and documents uploaded | Group
2014-08-23 |  | Work on Archival services | Carlo
2014-08-24 |  | Worked on Dynamic Jasper | Alfred
2014-08-25 |  | Refactored DB and updated DB Entities | Mathys
2014-08-26 |  | Application, and Person reports completed | Alfred
2014-08-26 |  | Found bugs, refactored to fix | Mathys
2014-08-27 |  | Front end and Back ends of reports completed | Alfred
2014-08-27 |  | Debugged user creation bugs and front and back ends of the bread crumbs | Mathys
2014-08-27 |  | Beans for archival services | Carlo
2014-08-28 |  | Created on demand approval, removal functions of CVs | Mathys
2014-08-29 |  | Fixed Bug in rewind, updated SQL entities | Mathys
2014-08-30 |  | Updated EBJs as per Client's request | Mathys
2014-08-31 |  | Included provisions for interceptors for unit tests | Alfred
2014-09-01 |  | Updated Authentication Interceptors and user gateway | Mathys
2014-09-02 |  | Front for exports and imports | Alfred
2014-09-03 |  | Updated referee reports, added interceptors for security | Mathys
2014-09-04 |  | Started DRIS approval refactorings | Mathys
2014-09-05 |  | Completed archival back up, fixed bugs | Alfred
2014-09-06 |  | Updated DRIS with client specifications, updated Meeting Managements | Mathys
2014-09-07 |  | Worked on dependencies found in the system | Alfred
2014-09-07 |  | Debugged refactorings, updated notifications | Mathys
2014-09-08 |  | Got Person entity working | Alfred
2014-09-08 |  | Refined XML schemas | Mathys
2014-09-09 |  | Application back up entities, person | Alfred
2014-09-09 |  | Added Transaction, annotation refactorings | Mathys
2014-09-10 |  | Updated EBJs and Daos | Alfred
2014-09-10 |  | Completed Refactorings | Mathys
2014-09-11 |  | Updated POM so files could update | Mathys
2014-09-12 |  | Demo 4 and documents uploaded | Group
2014-09-13
2014-09-14
2014-09-15
2014-09-16 |  | Provisional Usability Test information | Carlo
2014-09-17 |  | Created Announcements, changes to location front end | Mathys
2014-09-18 |  | Started Internationalization | Alfred
2014-09-19 |  | Editing User Acceptance tests | Carlo
2014-09-19 |  | Updating Internationalization | Alfred
2014-09-20 |  | Fixing Jasper back end, fixed interceptor bug | Mathys
2014-09-20 |  | Fixed issue with security roles | Alfred
2014-09-21 |  | UI changes, demo Data, internalization almost complete | Alfred
2014-09-21 |  | Completed Location front end | Mathys
2014-09-22 |  | Updated Unit and Integration tests | Carlo
2014-09-22 |  | Added functionality to notification bar, fixed bugs in notifications | Mathys
2014-09-22 |  | UI changes for password strength, added to internalization | Alfred
2014-09-23 |  | Re-did reporting front end, updated report styling and fixed bugs | Mathys
2014-09-24 |  | Chagned Bread crums menu, Add Jsoup for html scrapper | Mathys
2014-09-24 |  | Internalization of all strings done | Alfred
2014-09-25 |  | UI Updates | Alfred
2014-09-25 |  | SQL Scripts updates | Mathys
2014-09-26 |  | Completed Demo data | Alfred
2014-09-26 |  | Editing Testing documentation | Carlo
2014-09-26 |  | Completed Google scholar scrapper | Mathys
2014-09-26 |  | Demo 5 | Group
2014-09-27
2014-09-28
2014-09-29 |  | Project Management Documents updated | Carlo
2014-09-30 |  | Added SHA512 hashing to passwords | Alfred
2014-10-01 |  | Refined Vision Scope, workflow diagram | Mathys
2014-10-01 |  | Updated Interface diagrams | Alfred
2014-10-02 |  | Updated use case diagrams, and functional requirements | Mathys
2014-10-03 |  | Added Brochure | Carlo
2014-10-03 |  | Completed post conditions, use cases, software architecture, functional requirements | Mathys
2014-10-03 |  | Updated models, diagrams, JSOUP to tech | Alfred
2014-10-03 |  | Documentation iteration 5 | Group
2014-10-04
2014-10-05
2014-10-06 |  | Updated all notifications, that are sent, did hash refactorings | Mathys
2014-10-07
2014-10-08
2014-10-09
2014-10-10
2014-10-11
2014-10-12
2014-10-13
2014-10-14
2014-10-15
2014-10-16
2014-10-17
2014-10-18
2014-10-19
2014-10-20
2014-10-21
2014-10-22
2014-10-23
2014-10-24
2014-10-25
2014-10-26
2014-10-27
2014-10-28
2014-10-29
2014-10-30
2014-10-31
2014-11-01
2014-11-02
2014-11-03
2014-11-04
2014-11-05
2014-11-06
2014-11-07
2014-11-08
2014-11-09
2014-11-10
2014-11-11
2014-11-12
2014-11-13
2014-11-14
2014-11-15
2014-11-16
2014-11-17
2014-11-18
2014-11-19
2014-11-20
2014-11-21
2014-11-22
2014-11-23
2014-11-24
2014-11-25
2014-11-26
2014-11-27
2014-11-28
2014-11-29
2014-11-30
2014-12-01
2014-12-02
2014-12-03
2014-12-04
2014-12-05
2014-12-06
2014-12-07
2014-12-08
2014-12-09
2014-12-10
2014-12-11
2014-12-12
2014-12-13
2014-12-14
2014-12-15
2014-12-16
2014-12-17
2014-12-18
2014-12-19
2014-12-20
2014-12-21
2014-12-22
2014-12-23
2014-12-24
2014-12-25
2014-12-26
2014-12-27
2014-12-28
2014-12-29
2014-12-30
2014-12-31
2015-01-01
2015-01-02
2015-01-03
2015-01-04
2015-01-05
2015-01-06
2015-01-07
2015-01-08
2015-01-09
2015-01-10
2015-01-11
2015-01-12
2015-01-13
2015-01-14
2015-01-15
2015-01-16
2015-01-17
2015-01-18
2015-01-19
2015-01-20
2015-01-21
2015-01-22
2015-01-23
2015-01-24
2015-01-25
2015-01-26
2015-01-27
2015-01-28
2015-01-29
2015-01-30
2015-01-31
2015-02-01
2015-02-02
2015-02-03
2015-02-04
2015-02-05
2015-02-06
2015-02-07
2015-02-08
2015-02-09
2015-02-10
2015-02-11
2015-02-12
2015-02-13
2015-02-14
2015-02-15
2015-02-16
2015-02-17
2015-02-18
2015-02-19
2015-02-20
2015-02-21
2015-02-22
2015-02-23
2015-02-24
2015-02-25
2015-02-26
2015-02-27
2015-02-28
2015-03-01
2015-03-02
2015-03-03
2015-03-04
2015-03-05
2015-03-06
2015-03-07
2015-03-08
2015-03-09
2015-03-10
2015-03-11
2015-03-12
2015-03-13
2015-03-14
2015-03-15
2015-03-16
2015-03-17
2015-03-18
2015-03-19
2015-03-20
2015-03-21
2015-03-22
2015-03-23
2015-03-24
2015-03-25
2015-03-26
2015-03-27
2015-03-28
2015-03-29
2015-03-30
2015-03-31
2015-04-01
2015-04-02
2015-04-03
2015-04-04
2015-04-05
2015-04-06
2015-04-07
2015-04-08
2015-04-09
2015-04-10
2015-04-11
2015-04-12
2015-04-13
2015-04-14
2015-04-15
2015-04-16
2015-04-17
2015-04-18
2015-04-19
2015-04-20
2015-04-21
2015-04-22
2015-04-23
2015-04-24
2015-04-25
2015-04-26
2015-04-27
2015-04-28
2015-04-29
2015-04-30
2015-05-01
2015-05-02
2015-05-03
2015-05-04
2015-05-05
2015-05-06
2015-05-07
2015-05-08
2015-05-09
2015-05-10
2015-05-11
2015-05-12
2015-05-13
2015-05-14
2015-05-15
2015-05-16
2015-05-17
2015-05-18
2015-05-19
2015-05-20
2015-05-21
2015-05-22
2015-05-23
2015-05-24
2015-05-25
2015-05-26
2015-05-27
2015-05-28
2015-05-29
2015-05-30
2015-05-31
2015-06-01
2015-06-02
2015-06-03
2015-06-04
2015-06-05
2015-06-06
2015-06-07
2015-06-08
2015-06-09
2015-06-10
2015-06-11
2015-06-12
2015-06-13
2015-06-14
2015-06-15
2015-06-16
2015-06-17
2015-06-18
2015-06-19
2015-06-20
2015-06-21
2015-06-22
2015-06-23
2015-06-24
2015-06-25
2015-06-26
2015-06-27
2015-06-28
2015-06-29
2015-06-30
2015-07-01
2015-07-02
2015-07-03
2015-07-04
2015-07-05
2015-07-06
2015-07-07
2015-07-08
2015-07-09
2015-07-10
2015-07-11
2015-07-12
2015-07-13
2015-07-14
2015-07-15
2015-07-16
2015-07-17
2015-07-18
2015-07-19
2015-07-20
2015-07-21
2015-07-22
2015-07-23
2015-07-24
2015-07-25
2015-07-26
2015-07-27
2015-07-28
2015-07-29
2015-07-30
2015-07-31
2015-08-01
2015-08-02
2015-08-03
2015-08-04
2015-08-05
2015-08-06
2015-08-07
2015-08-08
2015-08-09
2015-08-10
2015-08-11
2015-08-12
2015-08-13
2015-08-14
2015-08-15
2015-08-16
2015-08-17
2015-08-18
2015-08-19
2015-08-20
2015-08-21
2015-08-22
2015-08-23
2015-08-24
2015-08-25
2015-08-26
2015-08-27
2015-08-28
2015-08-29
2015-08-30
2015-08-31
2015-09-01
2015-09-02
2015-09-03
2015-09-04
2015-09-05
2015-09-06
2015-09-07
2015-09-08
2015-09-09
2015-09-10
2015-09-11
2015-09-12
2015-09-13
2015-09-14
2015-09-15
2015-09-16
2015-09-17
2015-09-18
2015-09-19
2015-09-20
2015-09-21
2015-09-22
2015-09-23
2015-09-24
2015-09-25
2015-09-26
2015-09-27
2015-09-28
2015-09-29
2015-09-30
2015-10-01
2015-10-02
2015-10-03
2015-10-04
2015-10-05
2015-10-06
2015-10-07
2015-10-08
2015-10-09
2015-10-10
2015-10-11
2015-10-12
2015-10-13
2015-10-14
2015-10-15
2015-10-16
2015-10-17
2015-10-18
2015-10-19
2015-10-20